## Sheet1
Work Breakdown | [9 empty] | Status values: | Priority values
Category | Work Item | Status | Priority | Cost (hrs) | Start Date | End Date | Owner | Reviewer |  | Active | 1
Start screen | Graphics/Logo | Done, tested | 2 | 1 | 2023-05-19 | 2023-05-23 | Both | Fenix |  | Cut | 2
Start screen | Hook up buttons to Help and Start | Done, tested | 2 | 0.5 | 2023-05-20 | 2023-05-21 | Fenix | Veer |  | Done, not tested | 3
Start/In-Game | Popup class | Done, tested | 1 | 1 | 2023-05-22 | 2023-05-23 | Fenix | Veer |  | Done, tested
Help Screen | Pop up with text explanation of game | Done, tested | 2 | 0.2 | 2023-05-22 | 2023-05-22 | Fenix | Veer
In-Game | UI for game | Done, tested | 1 | 1 | 2023-05-19 | 2023-05-24 | Fenix | Veer
In-Game | Player class | Done, tested | 1 | 1 | 2023-05-23 | 2023-05-23 | Fenix | Veer
In-Game | Setting description and context | Done, not tested | 2 | 0.1 | 2023-06-03 | 2023-06-03 | Fenix | Veer
In-Game | Choice class | Done, tested | 2 | 1 | 2023-05-25 | 2023-05-26 | Fenix | Veer
In-Game | Encounter class | Done, tested | 1 | 1.5 | 2023-05-23 | 2023-05-25 | Fenix | Veer
In-Game | Game controller class / Encounters | Done, tested | 1 | 12 | 2023-05-25 | 2023-06-04 | Both | Both
Game over screen | Graphics, text, Try Again and Quit buttons | Done, tested | 1 |  | 2023-06-04 | 2023-06-04 | Veer | Fenix
In-Game | Ending (conditions to take the user to end screen) | Cut | 2 |  | - | - | Fenix | Veer | We decided to make the game simply end with death instead,
End screen | Graphics and text | Cut | 2 |  | - | - | Veer | Fenix | with a high score type of system
End screen | Hook up Play Again button | Cut | 2 |  | - | - | Veer | Fenix
In-Game | Generate or create art | Cut | 3 | 0 | - | - | Fenix | Veer | Unnecessary
In-Game | Add art images to game display | Cut | 3 | 0 | - | - | Veer | Fenix | Unnecessary